## Slide 1
Branding Team
JAS 2026 Review
& OND Plan
What we delivered in July – September, and what we commit to for October – December
Presented by [Presenter name]
30 Oct 2026 · Blue Iris
1,109
creatives delivered in JAS
6 live retainers
8 projects in the quarter
Notes: Open (15 sec): 'In the next 10 minutes: what the branding team delivered in July to September, how we score against our KPIs, and what we're committing to for Oct to Dec.'

## Slide 2: JAS at a glance: 1,109 creatives, 81% for retainers
1,109
creatives delivered
(Jul – Sep)
104
master creatives
(new concepts)
81%
of output went to
the 6 live retainers
6 / 8
projects closed
on time
TO ADD
Overall weighted KPI score for JAS (one number, e.g. 87%), plus one line on the biggest win and one on the biggest miss.
Watch-outs
TMB alone is 44% of all output: heavy reliance on one client
67% of master creatives came from one designer: key-person risk
2 projects slipped: Checkpoint Diagnostic, Xylemx
Notes: ~60 sec. Lead with the headline KPI score (fill the orange box). Then: 1,109 creatives, 104 of them new concepts. 81% of output (899 units) went to the 6 retainers: TMB, Star Health, VGN, TVS Credit, Maxivision, Athmalaya. Name the watch-outs yourself before anyone else does.

## Slide 3: TVS ads: committed last quarter, delivered this quarter
AMJ 2026
Committed to the client
JAS 2026
Concepts and production executed
Delivered
3 TVC commercial ads
Scope: 3 TVC commercial ads for TVS Green
Team: Gowtham (5 master concepts), Naresh (7 creatives)
Why it matters: we kept a commitment that carried across quarters, and it proves we can deliver video. That is the base for OND's push into real-estate AI videos.
TO ADD
2–3 stills or a 10-sec clip from the TVS ads, plus one line of client feedback (quote or approval email).
Notes: ~75 sec. This is the story to land. 'This was promised last quarter. We carried it over and delivered it this quarter.' Show the stills or clip. CHECK BEFORE PRESENTING: the project tracker still lists TVS Green 'TVC Commercial Ads - 3' as Oct / In-progress. Update the tracker to Completed or someone will catch the mismatch.

## Slide 4: Month-wise: July closed 4 projects, August slipped 2
Chart: Projects started per month, by status
| July | August | September
Completed | 4 | 1 | 1
In progress (delayed) | 0 | 2 | 0
Creatives | July | August | September
Target (projection) | [add] | [add] | [add]
Actually done | [add] | [add] | [add]
Achievement % | [add] | [add] | [add]
Quarter total | 1,109 creatives delivered (Jul–Sep) |  | 
TO ADD
Split the creative pivot by month (Jul / Aug / Sep) and add the target for each month. The agenda asks for a month-wise review.
Notes: ~60 sec. Projects by start month, from the project tracker. July: SBJH Founders Day, VKS Builders, SIP Academy 23-yr, Wewin Coimbatore (all done). August: JMI done; Checkpoint Diagnostic and Xylemx still in progress. September: Wewin Bangalore done. Fill the creatives table from a month-filtered pivot.

## Slide 5: KPI scorecard: projection vs. actually done
Weight 25%
On-Time Project Delivery
75%
Amber
6 of 8 projects delivered on time
Source: PixDo / project tracker
Weight 30%
Design & Creatives outcomes
150%
Green
841 units vs. 561 in retainer scope*
Source: Branding Team Scrum Tracker
Weight 5%
Attendance / Production days
TO ADD
Leave days ÷ total working days, from the PixDo leave report.
* Scope = TMB, VGN, Star Health, Maxivision, Athmalaya for 3 months. Counts adaptations; the next slide shows why that matters. Score capped at 100% when weighted.
Notes: ~75 sec. KPI method = projection vs. actually done. On-time: 8 projects in JAS, 6 on time; Checkpoint Diagnostic and Xylemx slipped. Design & Creatives: planned = retainer scope (561 units), done = 841. Upsell, Project Retention and CSAT are deliberately left off this slide. Be ready if asked: 'We start tracking them from OND with a defined source.'

## Slide 6: Retainer delivery vs. scope: one definition decides it
Retainer | Scope / month | JAS scope | Creatives + masters | Adaptations | Total | % of scope (all) | % excl. adaptations
TMB Bank | 70 | 210 | 170 | 321 | 491 | 234% | 81%
VGN Homes | 35 | 105 | 112 | 19 | 131 | 125% | 107%
Star Health | 70 units | 210 | 64 | 111 | 175 | 83% | 30%
Maxivision | 6–10 | 18–30 | 40 | 1 | 41 | 137% | 133%
Athmalaya | 2 posts | 6 | 3 | 0 | 3 | 50% | 50%
TVS Credit | 4 newsletters / yr | ~1 newsletter | 58 | 0 | 58 | confirm unit | confirm unit
Decide before presenting: do adaptations count toward retainer scope? If they do, TMB is at 2.3× scope, which may be unbilled over-delivery. If they don't, TMB is under scope at 81% and Star Health at 30%.
Notes: ~75 sec. Scope comes from the retainer tracker × 3 months. Delivered = JAS creative pivot by client. Present ONE of the two % columns once the definition is agreed, and delete the other. Athmalaya at 3 of 6 posts is a real shortfall either way. Have the reason ready. Star Health's scope says '70 creative units = 35–40 creatives', so confirm how a unit is counted.

## Slide 7: Team output by type: new concepts sit with one person
Chart: Units delivered in JAS, by person and type
| Ezhumalai | Gowtham | Keerthana | Naresh
Master creatives | 5 | 70 | 6 | 23
Creatives | 101 | 118 | 91 | 199
Adaptations | 93 | 11 | 302 | 90
67%
of master creatives came from Gowtham (70 of 104). Concept work depends on one person.
76%
of Keerthana's 399 units are adaptations: the high-volume production line.
199
creatives from Naresh, the most of any designer.
Notes: ~60 sec. Totals: Ezhumalai 199, Gowtham 199, Keerthana 399, Naresh 312. Don't rank people by raw volume: a master creative is not equal to an adaptation. If asked for a ranking, use a weighting agreed with leadership beforehand. Key-person risk: name the OND mitigation (e.g., a second designer pairs on concepts).

## Slide 8: Projects in JAS: 6 closed, 2 slipped
Month | Client | Scope | Status
Jul | SBJH Founders Day | Event collaterals: standee, stage LED, videos | Completed
Jul | VKS Builders | Brand logo design & stationery | Completed
Jul | SIP Academy | 23-year anniversary event collaterals | Completed
Jul | Wewin Automation | B-card & event panels, Coimbatore (11) | Completed
Aug | JMI | Event posters (10) & 12-page catalogue | Completed
Aug | Checkpoint Diagnostic | Re-branding | Delayed
Aug | Xylemx | Logo design | Delayed
Sep | Wewin Automation | Event panel adaptation, Bangalore (7) | Completed
Why 2 slipped
TO ADD
Reason per project (approvals, scope change, inputs) + new close date.
Pitch support (not in the tracker)
Apollo and DBS pitches: 9 master creatives
TO ADD
Outcome: won / lost / pending
Notes: ~60 sec. 6 of 8 projects closed. Checkpoint Diagnostic and Xylemx started in August and are still open at the end of October. Give the reason and the new close date, not an apology. The pitch work (Apollo, DBS) used real concept capacity. Say whether it converted.

## Slide 9: OND focus: real-estate AI videos and AI-led creative
Real-estate AI videos
Turn the TVS TVC capability and 3D rendering into AI video offers for real-estate clients.
AI-led creative
Use AI tools to speed up concepts and adaptations, and package them as new deliverables.
Close & protect
Close Checkpoint, Xylemx and TVS Green; keep every retainer on scope.
Target | Oct (actual) | Nov | Dec
Real-estate AI videos delivered | [add] | [add] | [add]
AI-led creative deliverables | [add] | [add] | [add]
Retainer delivery vs. scope | [add] | [add] | [add]
On-time project delivery | [add] | [add] | [add]
Notes: ~75 sec. October is almost over, so the Oct column should be actuals, not a plan. Give each AI target a number and an owner. If there's an ask (tools budget, a hire, a decision on billing TMB's over-scope work), say it here.

## Slide 10
Thank you
Questions and discussion
Branding Team · JAS 2026
Ezhumalai
Gowtham
Keerthana
Naresh
Notes: Close on the OND commitments. Supporting data is in the appendix if asked.

## Slide 11: Appendix: where the 1,109 creatives went
Chart: Total units (masters + creatives + adaptations) by client, JAS 2026
| TMB Bank | Star Health | VGN Homes | TVS Credit | SIP Academy | Maxivision | Wewin | Teamware | Pixel | Grocers | 12 others
Units | 491 | 175 | 131 | 58 | 42 | 41 | 27 | 22 | 16 | 15 | 91
Notes: Backup only. 12 others: Checkpoint 10, Skylink 13, JMI 12, SBJH 12, TVS Green 12, Rakki 8, DBS pitch 8, VKS 7, Xylemx 4, Athmalaya 3, Care AKPS 1, Apollo pitch 1.

## Slide 12: Appendix: KPI definitions and data sources
KPI | Weight | How it is measured | Data source
On-Time Project Delivery | 25% | Projects delivered on time ÷ total due × 100 | PixDo
Design & Creatives outcomes | 30% | Planned deliverables completed ÷ planned × 100 | Branding Team Scrum Tracker
Attendance / Production days | 5% | Leave availed ÷ total working days × 100 | PixDo Leave report
Retainer scope | n/a | Monthly scope per retainer × 3 = JAS projection | Retainer & project tracker
TO ADD
Links to the backing reports (PixDo export, Scrum Tracker, creative pivot, leave report), so every number on the KPI slides can be traced.
Notes: Covers the agenda item 'Documentation & supporting metrics'. Keep the links ready on the laptop in case someone asks to see the source.